## ProjectSchedule
Tasdeeq - Digital Verification Platform
[Tasdeeq] |  | Project Start: | 2026-02-02
[Fazeel Ahmed] |  | Today: | 2027-05-31
|  | Display Week: | 2 |  |  | 2026-02-09 | [6 empty] | 2026-04-20 | [6 empty] | 2026-06-29 | [6 empty] | 2026-09-07 | [6 empty] | 2026-11-16 | [6 empty] | 2027-01-25 | [6 empty] | 2027-04-05 | [6 empty] | 2027-06-14
 | time axis 2026-02-09 to 2027-08-13
TASK | ASSIGNED TO | Duration | START | END | DAYS | time axis 2026-02-09 to 2027-08-13
Requirement Phase
Requirements Analysis |  | 28 days | 2026-02-02 | 2026-02-28 | 27
Documentation |  | 30 days | 2026-03-01 | 2026-04-30 | 61
Design Phase
System Architecture |  | 30 days | 2026-05-01 | 2026-05-30 | 30
DB Schema |  | 30 days | 2026-06-01 | 2026-06-30 | 30
UI/UX Design |  | 60 days | 2026-07-01 | 2026-08-30 | 61
Development Phase
Frontend Development |  | 60 days | 2026-09-01 | 2026-10-30 | 60
Backend Development |  | 90 days | 2026-11-01 | 2027-01-30 | 91
Integration and Testing Phase
Unit Testing |  | 15 days | 2027-02-01 | 2027-02-15 | 15
Integration Testing |  | 15 days | 2027-02-16 | 2027-02-28 | 13
User Acceptance Testing |  | 30 days | 2027-03-01 | 2027-03-30 | 30
Deployment Phase
Final Review and Deploment |  | 60 days | 2027-04-01 | 2027-05-31 | 61
Note on H6: DAYS: This column calculates the duration of the task in calendar days. The duration includes both the Start and End dates.